## Sheet1
Type | Item |  | Week 1 |  |  | Week 2 |  |  | Week 3 |  |  | Week 4 |  |  | Week 5 |  |  | Week 6
|  | 2024-11-01 | 2024-11-04 | 2024-11-06 | 2024-11-08 | 2024-11-11 | 2024-11-13 | 2024-11-15 | 2024-11-18 | 2024-11-20 | 2024-11-22 | 2024-11-25 | 2024-11-27 | 2024-11-29 | 2024-12-02 | 2024-12-04 | 2024-12-06 | 2024-12-09 | 2024-12-11
Bootup Arduino | bar: 2024-11-01 to 2024-11-04
Install Thonny | bar: 2024-11-01 to 2024-11-04
Configure Minipython | bar: 2024-11-01 to 2024-11-04
Buy EcEn shop parts | bar: 2024-11-01 to 2024-11-04
CAD: find Linear Actuator model | bar: 2024-11-01 to 2024-11-08
CAD: adjust model for our system | bar: 2024-11-01 to 2024-11-08
Print gears | bar: 2024-11-01 to 2024-11-08
Test gearing w/motors | bar: 2024-11-06 to 2024-11-11
Configure motors (on/off) | bar: 2024-11-06 to 2024-11-11
Configure motors (PWM) | bar: 2024-11-08 to 2024-11-13
Determine y_min detector | bar: 2024-11-11 to 2024-11-13
Configure single US sensor | bar: 2024-11-13
Configure dual US sensors | bar: 2024-11-13
Test limit signal | bar: 2024-11-15
Simultaneous component test | bar: 2024-11-15
Source trough and ball | bar: 2024-11-18 to 2024-11-20
Size system based on: - Actuator limits - US sensor limits - Trough+ball mass | bar: 2024-11-18 to 2024-11-20
Confirm I/O | bar: 2024-11-18 to 2024-11-20
Test US sensor reading | bar: 2024-11-18 to 2024-11-20
Implement US filters | bar: 2024-11-18 to 2024-11-20
Create "getDavg" function | bar: 2024-11-18 to 2024-11-20
Test vertical limit enforcer reading | bar: 2024-11-18 to 2024-11-20
Create "check limit" function | bar: 2024-11-18 to 2024-11-20
Test motor actuation from code | bar: 2024-11-18 to 2024-11-20
Create "move" function | bar: 2024-11-18 to 2024-11-20
Due | Proposal | bar: 2024-11-22
Assemble system | bar: 2024-11-22 to 2024-11-25
Create UI: - Auto/manual modes - Manual mode motor buttons | bar: 2024-11-22 to 2024-11-25
Test system with manual operation | bar: 2024-11-27 to 2024-11-29
Test y_min enforcement | bar: 2024-11-27 to 2024-11-29
Test y_max behavior | bar: 2024-11-27 to 2024-11-29
Test US sensor readings | bar: 2024-11-27 to 2024-11-29
Create main PID loop in code | bar: 2024-11-27 to 2024-11-29
Determine model for control loop | bar: 2024-12-02 to 2024-12-04
DOE to determine tuning params | bar: 2024-12-02 to 2024-12-04
Determine PID parameters | bar: 2024-12-02 to 2024-12-04
Due | Update 1 | bar: 2024-12-04
Fune tuning | bar: 2024-12-04 to 2024-12-06
Due | Update 2
Due | Update 3 | bar: 2024-12-09
Due | Report | bar: 2024-12-11
Due | Presentation | bar: 2024-12-11
Due | Code & Hardware | bar: 2024-12-11
Note on B17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Does I/O still work well with all components operating?